## Sheet1
Week plan for Garuda project.
Date | Task Description | Remarks
2022-03-29 | Introduction to OpenCv Connection with Flask application
2022-03-30 | Test a use case of Line Crossing on live streaming using Flask web server
2022-03-31 | Test a use case of individual and multiple Loitering on live streaming using Flask web server
2022-04-01 | Test a use case of vehicle detection on live steaming using Flask web server
2022-04-04 | Test a use case of abandoned object on live streaming using Flask web server
2022-04-05 | Finalize all the use case with configurable with all the camera individually or together
2022-04-06 | Connect Front end application with use camera mapping and check the Live Streaming.
2022-04-07 | Solve the bugs and development on Video analytics and connect with MySQL Database
2022-04-08 | Create Alert message in user interface on angular project.